## Sheet1
Task ID | Task Name | Duration | Start | Finish | Done | Predecessors | Resource Names
1 | Requirement Analysis & Definition | 5 days | Thu 19-02-28 | Wed 19-03-06 | o
2 | Requriement analysis | 2 days | Thu 19-02-28 | Fri 19-03-01 | o |  | Chansin,James,Murphy,Quang,Rolando
3 | Planning a schedule and roles | 2 days | Mon 19-03-04 | Tue 19-03-05 | o | 2 | James
4 | UML use case diagram(W2) | 1 day | Mon 19-03-04 | Mon 19-03-04 | o | 2 | Quang,Rolando,James
5 | UML use case specification(W2) | 2 days | Tue 19-03-05 | Wed 19-03-06 | o | 4 | Murphy,Chansin,Quang,Rolando
6 | Requirement is defined | 0 days | Wed 19-03-06 | Wed 19-03-06 | o | 5
7 | Website Design | 8 days | Thu 19-03-07 | Mon 19-03-18 | o | 6
8 | Layout | 3 days | Thu 19-03-07 | Mon 19-03-18 | o
9 | Draw diagrams | 3 days | Thu 19-03-07 | Mon 19-03-11 | o |  | Quang,Murphy,Rolando
10 | Prepare pictures | 2 days | Thu 19-03-07 | Fri 19-03-08 | o |  | Rolando,Murphy
11 | Build Website | 3 days | Tue 19-03-12 | Thu 19-03-14 | o
12 | Create customer page | 3 days | Tue 19-03-12 | Thu 19-03-14 | o | 9 | Quang
13 | Create restaurant page | 2 days | Tue 19-03-22 | Wed 19-03-28 | o | 9 | Changsin,Rolando
14 | Create administrator page | 2 days | Tue 19-03-12 | Wed 19-03-13 | o | 9 | Rolando
15 | Desing Webpage | 2 days | Fri 19-03-15 | Mon 19-03-18 | o | 11
16 | CSS | 2 days | Fri 19-03-15 | Mon 19-03-18 | o |  | Quang
17 | Button/links | 2 days | Fri 19-03-15 | Mon 19-03-18 | o |  | Rolando
18 | Database Design | 5 days? | Thu 19-03-07 | Wed 19-03-13 | o | 6
19 | Create entities | 2 days | Thu 19-03-07 | Fri 19-03-08 | o |  | James,Chansin
20 | Normalization | 2 days | Mon 19-03-11 | Tue 19-03-12 | o | 19 | James,Murphy
21 | SQL script objects and create DB(W3) | 1 day? | Wed 19-03-13 | Wed 19-03-13 | o | 20 | James,Murphy
22 | Preparation for development | 0 days | Mon 19-03-18 | Mon 19-03-18 | o | 7,18
23 | Database Development | 4 days | Thu 19-03-14 | Tue 19-03-19 | o
24 | Define variables(Product, Order, Restaurant Info) | 1 day | Thu 19-03-14 | Thu 19-03-14 | o |  | Murphy
25 | Insert master data(W4) | 1 day | Fri 19-03-15 | Fri 19-03-15 | o | 24 | Murphy
26 | Write Quries(product, order, review, rating) | 2 days | Mon 19-03-18 | Tue 19-03-19 | o | 25 | James
27 | Implement customer pages | 15 days? | Thu 19-03-14 | Wed 19-04-03 | -
28 | Display products information | 15 days | Thu 19-03-14 | Wed 19-04-03 | o
29 | Display products(W4) | 3 days | Thu 19-03-14 | Mon 19-03-18 | o |  | Chansin,Murphy,James
30 | Display product recommendation(W7) | 2 days | Tue 19-04-02 | Wed 19-04-03 | - |  | Murphy
31 | Rate(W6) and review(W5) | 2 days | Mon 19-03-25 | Tue 19-03-27 | o |  | Murphy
32 | Shopping cart | 12 days? | Thu 19-03-14 | Fri 19-03-29 | o
33 | Display products(W5) | 2 days | Thu 19-03-21 | Fri 19-03-24 | o |  | James
34 | Add products(W5) | 2 days | Thu 19-03-21 | Fri 19-03-26 | o | 33 | James
35 | Remove products(W6) | 1 day? | Thu 19-03-28 | Thu 19-03-28 | o | 33 | Quang
36 | Modify quantity(W6) | 1 day? | Fri 19-03-29 | Fri 19-03-29 | o | 33 | Quang
37 | Checkout | 3 days? | Mon 19-03-25 | Wed 19-03-27 | o
38 | Billing/Shipping Form (W6) | 2 days | Mon 19-03-25 | Tue 19-03-26 | o |  | Rolando
39 | Validation (W6) | 1 day? | Tue 19-03-26 | Tue 19-03-26 | o |  | Rolando
40 | Create a file for the receipt (W6) | 1 day? | Wed 19-03-27 | Wed 19-03-27 | o |  | Rolando
41 | Display order history (W7) | 2 days | Mon 19-04-01 | Tue 19-04-02 | o |  | Rolando, Murphy
42 | Privacy agreement | 2 days | Thu 19-03-28 | Fri 19-03-29 | o |  | James
43 | Implement restaurant pages | 3 days? | Tue 19-03-19 | Thu 19-03-21 | o
44 | Display order | 1 day? | Tue 19-03-19 | Tue 19-03-19 | o |  | Chansin,Rolando
46 | Modify order status | 1 day? | Wed 19-03-20 | Wed 19-03-20 | o | 43 | Chansin, Rolando
47 | Implement administrator pages | 3 days | Thu 19-03-14 | Mon 19-03-18 | o
48 | Manage restaurants and products(W4) | 3 days | Thu 19-03-14 | Mon 19-03-18 | o |  | James
49 | Login page(W5) | 2 days | Thu 19-03-21 | Fri 19-03-22 | o
50 | Register account(W5) | 2 days | Thu 19-03-21 | Fri 19-03-26 | o |  | Chansin
51 | Authentication(W5) | 2 days | Thu 19-03-21 | Fri 19-03-26 | o |  | Rolando
52 | Customers Recommendation(W7) | 2 days | Thu 19-03-28 | Wed 19-04-02 | - |  | Murphy
53 | Completion of Implementation | 0 days | Wed 19-04-03 | Wed 19-04-03 | - | 27,42,46,48
54 | Integrated Test | 5 days | Thu 19-04-04 | Wed 19-04-10 | -
55 | Test cases | 2 days | Thu 19-04-04 | Fri 19-04-05 | - |  | Changsin
56 | Testing | 2 days | Mon 19-04-08 | Tue 19-04-09 | - | 54 | Chansin,Murphy
57 | Debugging | 1 day | Wed 19-04-10 | Wed 19-04-10 | - | 55 | James,Rolando
58 | Ready fo final presentation | 0 days | Wed 19-04-10 | Wed 19-04-10 | - | 53
59 | Final Presentation | 1 day | Thu 19-04-11 | Thu 19-04-11 | - | 53
| Final Report | 1 day | Thu 19-04-11 | Thu 19-04-11 | - |  | Quang