## Tasks
Week | Task ID | Document for submit | Member | Demo Requirement
1 | W11 | Project Charter | ChangSin, Rolando
1 | W12 | BRD | Quang, Murphy, James | BRD
1 | W13 | Task Log | James
1 | W14 | Weekly Status | James | Weekly Status

## Roles
Week | Team Lead | DBA/Back-End developer | Middle-ware developer | Front-End developer | Technical Writer
2 | J | C | R | Q | J
3 | M | C | R | Q | J
4 | C | M | Q | R | J
5 | R | M | C | Q | R
6 | Q | R | J | C | M
7 | J | Q | R | M | C
8 | Q | J | R | M | C

## Meeting Notes
No | Activity
1 | Regular meeting on Friday at 1pm
2
3
4
5
6
7
8
9
10
11
12
13
14
15

## Check List
Task ID | Category | Tasks | Start Week | End Week | ALL | C | R | Q | M | J | Finish | Remark
1 |  | Used at MS Project | 1 | 1 | O
2 |  | Used at GitLab | 2 | 2 | O
3 |  | Project Charter | 1 | 1.5 |  | O | O
4 |  | BRD-draft | 1 | 1.5 |  |  |  | O | O | O
5 |  | Task Log | 1 | 1.5 | [5 empty] | O |  | Google Document
6 |  | Weekly Status | 1 | 1.5 | [5 empty] | O
7 |  | Define Roles | 1 | 1 | O | [5 empty] | Y
8 |  | Read current requirements | 1 | 1 | O
9 |  | Gantt Chart | 1 | 1.5 | [5 empty] | O
10 |  | UML
11 |  | UX Design
12 |  | BugJila, JIRA
13 |  | Check shared account on deepblue
14 |  | Test Cases
15 |  | Consider to use Bootstrap
16 |  | Kick off
17 |  | Data Modelling
18 |  | Cadence Meeting | 1 | 7 | O
19
20
21
22
23
24
25
26
27
28
29