## Sheet1
Website design
Layout
Draw diagrams
Customer page | Quang | before Sunday
Restaurant page | Rolando | before Sunday
Admin page | Changsin | before Sunday
prepare pictures |  |  | Go to PRINT and click resize
Japanese food | Rolando | 3 restaurants and 5 pictures each | 200*200
Korean food | James | 3 restaurants and 5 pictures each
Chinese food | Murphy | 3 restaurants and 5 pictures each
Italy food | Rolando | 3 restaurants and 5 pictures each
Canadian food | Changsin | 3 restaurants and 5 pictures each
Vietnamese food | Quang | 3 restaurants and 5 pictures each
Use html to design Website
Customer page | Quang | before thursday
restaurant page | Rolando | before thursday
Administrator page | Changsin | before thursday
Database Design
creat entities | James, Chnagsin, Murphy | before Tuesday
Normalizations | James, Chnagsin, Murphy | before Tuesday
SQL script objects and creat DB | James, Chnagsin, Murphy | before Tuesday
document
BRD | Murphy
task log | everybody
GIT repository | everybody
Weekly status | everybody
Git repository report | Murphy
Weekly status report | Murphy
Tec writer | James